# Epic Breakdown & Development Plan

# AI Game Asset Factory

Version 1.0

# Project Goals

Deliver a local-first desktop application capable of generating, processing, organizing, and exporting game-ready 2D assets using AI while respecting an 8 GB VRAM constraint.

Target User: Solo Game Developer

Target Platform: Windows Desktop

Target Hardware: RTX 4070 Laptop GPU 32 GB RAM

# Team Structure

Recommended Team

1 Technical Lead

2 AI / Computer Vision Engineers

1 Full Stack Desktop Developer

1 QA Engineer

Optional: 1 UX/UI Designer

# Development Phases

Phase 0 Architecture & Validation

Phase 1 Foundation Platform

Phase 2 Asset Generation Pipeline

Phase 3 Asset Processing Pipeline

Phase 4 Export Pipeline

Phase 5 Animation Pipeline

Phase 6 Optimization & Release

# EPIC 1

Project Foundation

Priority: Critical

Dependencies: None

Objective: Create the application framework and project management system.

User Stories

US-001

As a user I want to create a project so that I can organize generated assets.

Acceptance Criteria

- Project created successfully

- Folder structure generated

- Database record created

US-002

As a user I want to open existing projects.

Acceptance Criteria

- Project loads successfully

- Assets appear correctly

US-003

As a user I want to delete projects.

Acceptance Criteria

- Project removed

- Associated records removed

Technical Tasks

TASK-001

Create SQLite schema

TASK-002

Implement ProjectService

TASK-003

Implement ProjectRepository

TASK-004

Implement Dashboard UI

Estimated Effort

2 weeks

# EPIC 2

Style Profile System

Priority: Critical

Dependencies: Epic 1

Objective: Guarantee style consistency across generations.

User Stories

US-010

Create style profile

US-011

Edit style profile

US-012

Apply style profile automatically

Technical Tasks

TASK-010

Style profile schema

TASK-011

Prompt composer

TASK-012

Reference image storage

TASK-013

Style profile UI

Estimated Effort

2 weeks

# EPIC 3

AI Asset Generation

Priority: Critical

Dependencies: Epic 1 Epic 2

Objective: Generate consistent game assets.

User Stories

US-020

Generate character

US-021

Generate environment asset

US-022

Generate prop

US-023

Generate building

US-024

Generate tileset

Technical Tasks

TASK-020

Stable Diffusion integration

TASK-021

Model manager

TASK-022

VRAM monitoring

TASK-023

Generation workflow

TASK-024

Generation preview UI

TASK-025

Batch generation

Estimated Effort

3 weeks

# EPIC 4

Background Removal

Priority: High

Dependencies: Epic 3

Objective: Produce transparent game-ready assets.

User Stories

US-030

Remove background automatically

US-031

Batch remove backgrounds

Technical Tasks

TASK-030

Rembg integration

TASK-031

Background service

TASK-032

Batch processing

Estimated Effort

1 week

# EPIC 5

Sprite Extraction

Priority: High

Dependencies: Epic 4

Objective: Extract individual assets from sheets.

User Stories

US-040

Extract sprites automatically

US-041

Auto-name assets

US-042

Review extraction results

Technical Tasks

TASK-040

Contour detection

TASK-041

Bounding box generation

TASK-042

Asset cropping

TASK-043

Naming engine

Estimated Effort

2 weeks

# EPIC 6

Metadata & Classification

Priority: Medium

Dependencies: Epic 5

Objective: Automatically organize assets.

User Stories

US-050

Generate metadata

US-051

Classify asset types

US-052

Search by asset category

Technical Tasks

TASK-050

Metadata schema

TASK-051

CLIP integration

TASK-052

Classification engine

Estimated Effort

2 weeks

# EPIC 7

Texture Processing

Priority: Medium

Dependencies: Epic 5

Objective: Generate seamless textures.

User Stories

US-060

Create seamless tile

US-061

Preview tile

US-062

Export tile

Technical Tasks

TASK-060

Texture offset engine

TASK-061

Seam generation

TASK-062

Tile validator

Estimated Effort

1 week

# EPIC 8

Export System

Priority: Critical

Dependencies: Epic 6

Objective: Export assets in game-ready formats.

User Stories

US-070

Export project

US-071

Export selected assets

US-072

Export metadata

Technical Tasks

TASK-070

Export service

TASK-071

Folder structure generation

TASK-072

Manifest generation

Estimated Effort

1 week

# EPIC 9

Animation Pipeline

Priority: High

Dependencies: Epic 3

Objective: Generate reusable game animations.

User Stories

US-080

Generate idle animation

US-081

Generate walk cycle

US-082

Generate run cycle

US-083

Generate attack animation

US-084

Generate death animation

Technical Tasks

TASK-080

Animation model integration

TASK-081

Loop validator

TASK-082

GIF exporter

TASK-083

Sprite sheet exporter

Estimated Effort

4 weeks

# EPIC 10

Workflow Automation

Priority: Critical

Dependencies: All previous epics

Objective: Enable one-click execution.

User Stories

US-090

Run complete pipeline

US-091

Monitor progress

US-092

Cancel execution

Technical Tasks

TASK-090

Workflow engine

TASK-091

Job queue

TASK-092

Progress tracking

TASK-093

Error recovery

Estimated Effort

2 weeks

# EPIC 11

Performance Optimization

Priority: Critical

Dependencies: All previous epics

Objective: Respect 8 GB VRAM budget.

User Stories

US-100

Monitor memory usage

US-101

Prevent VRAM crashes

US-102

Recover from failures

Technical Tasks

TASK-100

Model unloading system

TASK-101

VRAM profiler

TASK-102

Memory watchdog

TASK-103

Performance dashboard

Estimated Effort

2 weeks

# EPIC 12

Release Preparation

Priority: Critical

Dependencies: All previous epics

Objective: Ship a stable product.

Technical Tasks

TASK-110

Packaging

TASK-111

Installer

TASK-112

Model downloader

TASK-113

Configuration wizard

TASK-114

User documentation

TASK-115

QA validation

Estimated Effort

2 weeks

# Sprint Plan

Sprint 1

- Epic 1

- Epic 2

Deliverable: Working project system

Sprint 2

- Epic 3

Deliverable: Asset generation

Sprint 3

- Epic 4

- Epic 5

Deliverable: Transparent extracted assets

Sprint 4

- Epic 6

- Epic 7

Deliverable: Organized assets and tiles

Sprint 5

- Epic 8

- Epic 10

Deliverable: Complete one-click pipeline

Sprint 6

- Epic 9

Deliverable: Animation generation

Sprint 7

- Epic 11

Deliverable: Performance optimization

Sprint 8

- Epic 12

Deliverable: Release Candidate

# Release Definition

Version 1.0 Release Criteria

✓ Project Management Complete

✓ Style Profiles Complete

✓ Asset Generation Complete

✓ Background Removal Complete

✓ Sprite Extraction Complete

✓ Metadata Complete

✓ Texture Generation Complete

✓ Export Complete

✓ Animation Complete

✓ One-Click Workflow Complete

✓ Runs Offline

✓ Stable on RTX 4070 Laptop GPU

✓ VRAM Usage Below 8 GB